## **Research and Adoption: Jobspeaker Pilot & CRM Research (regional decision)**

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Jun | Jul | Aug | Sept | Oct | Nov | Dec |
| * Pilot data collection
* Mapping activities
* Submit interim pilot report
* Research CRMs in use
 | * Pilot data collection
* Mapping activities
* Refine CRM requirements
 | * Pilot data collection
* Finalize CRM requirements and rubric
 | * Pilot data collection
* Evaluate leading CRM tools
* Submit CRM recommendations
 | * Pilot data collection
* Work with pilot colleges on post-pilot needs
 | * Submit final pilot report
* Develop plans for end of pilot licenses
 | * Transition activities from pilot licenses to full implementation
 |

## **Research, Evaluation, and Dissemination: Career Exploration & Student Success Tools/Technologies (local decision)**

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Jun | Jul | Aug | Sept | Oct | Nov | Dec |
| * Research CEX technology options and develop product dossiers
 | * Finalize CEX product dossiers
* Research existing SS tools use
* Update SS product dossiers
 | * WG3 meeting to evaluate CEX products
* Develop recommendations for SS tool features and use of tools
 | * Support colleges as requested in assessing technology options to meet recommendations and college needs
 | * Support colleges as requested in assessing technology options to meet recommendations and college needs
 | * Inform year 2 PN plans as they relate to technology adoption
 |  |