## **Research and Adoption: Jobspeaker Pilot & CRM Research (regional decision)**

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Jun | Jul | Aug | Sept | Oct | Nov | Dec |
| * Pilot data collection * Mapping activities * Submit interim pilot report * Research CRMs in use | * Pilot data collection * Mapping activities * Refine CRM requirements | * Pilot data collection * Finalize CRM requirements and rubric | * Pilot data collection * Evaluate leading CRM tools * Submit CRM recommendations | * Pilot data collection * Work with pilot colleges on post-pilot needs | * Submit final pilot report * Develop plans for end of pilot licenses | * Transition activities from pilot licenses to full implementation |

## **Research, Evaluation, and Dissemination: Career Exploration & Student Success Tools/Technologies (local decision)**

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Jun | Jul | Aug | Sept | Oct | Nov | Dec |
| * Research CEX technology options and develop product dossiers | * Finalize CEX product dossiers * Research existing SS tools use * Update SS product dossiers | * WG3 meeting to evaluate CEX products * Develop recommendations for SS tool features and use of tools | * Support colleges as requested in assessing technology options to meet recommendations and college needs | * Support colleges as requested in assessing technology options to meet recommendations and college needs | * Inform year 2 PN plans as they relate to technology adoption |  |